## Sheet1
[10 empty] | Tested By | [5 empty] | o d
[5 empty] | group 1 (Group 25) | group 2 (Group 26) | group 3 (Group 27) | group 4 (Group 28) | group 5 (Group 29) | group 6 (Group 30) | group 7 (Group 31) | group 8 (Group 32) | group 9 (Group 33) | group 10 (Group 34) | group 11 (Group 35) | group 12 (Group 36)
ID | Group | Requirement | Implemented In | UI XREF
cut and paste the screenshot of each page in this part of the spreadsheet, please. use as much space is needed.
1 | 34 | BOT II shall return a list of game move(s) to game manager | uta.cse3310.Bot.BotII.sendMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
2 | 34 | Bot II shall receive the game board from the gamemanger | uta.cse3310.Bot.BotII.requestMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 1, Steps 1-5 | Unable to test
3 | 34 | Bot II shall implement a fixed strategy against either BotI or person to determine what move(s) should be made | uta.cse3310.Bot.BotII.implementBotStrategy |  | Unable to Test |  |  |  |  | Unable To Test |  |  |  | Not Testable | This is not testable by the user | Unable to test
4 | 34 | Bot II shall be able to capture pieces | uta.cse3310.Bot.BotII.implement BotStrategy |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 2, Steps 1-3 | Start a game player vs bot. Move one of your pieces towards the bot's pieces. The bot will then capture your piece when your piece is adjacent to one of it's pieces.
5 | 34 | Bot II shall follow game rules of checkers according to https://en.wikipedia.org/wiki/English_draughts | uta.cse3310.Bot.BotII.determineMoves |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 2, Steps 1-3 | Start a game player vs bot. Play normally, the bot should only be able to make the same move the player is able to make.
6 | 34 | BotII shall be able to make one or more moves on the given game board/state | uta.cse3310.Bot.BotII.determineMoves |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 2, Steps 1-3 | Start a game player vs bot. Set up your pieces in a way that would allow for the bot to have a double jump or higher. Let the bot approach. The bot should then jump and be forced to make a double jump or higher.
7 | 34 | Bot II shall be given a request to make its move and return its move within the same function call | uta.cse3310.Bot.BotII.requestMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 2, Steps 1-3 | Unable to test
8 | 34 | Bot II shall evaluate multiple different moves | uta.cse3310.Bot.BotII.determineMoves |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 2, Steps 1-2 | Unable to test
9 | 34 | BotII shall be able to play against BotI with the same interface | uta.cse3310.Bot.BotII.requestMove |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 3: steps 4-8 | Test 3, Steps 1-3 | User logs into website. Start a game bot vs bot. The bots should play each other until one of them wins or a draw occurs.
10 | 34 | BotII shall be able handle logic where a piece is a king | uta.cse3310.Bot.BotII.determineMoves |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 2,Steps 1-3 | Unable to test
11 | 34 | BotII Shall assign a basic elo rating to each set of moves (normal, jump move) | uta.cse3310.Bot.BotII.determineMoves |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable | Unable to test
12 | 34 | BotII shall ensure the move attempted is valid move | uta.cse3310.Bot.BotII.isValidMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is redundant, we already have req 6 | Unable to test
13 | 34 | BotII shall ensure it can check both ways to move (diagonal left, diagonal right) | uta.cse3310.Bot.BotII.checkSingleMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | The user cannot control what moves the Bots actually chooses, therefore this cannot be tested | Unable to test
14 | 34 | BotII shall be able to check the validity of a normal move and a jump/capture move | uta.cse3310.Bot.BotII.isValidMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 2, steps 1-4 | Unable to test
15 | 34 | BotII shall be able to determine how many moves or rows a piece is away from becoming a king after a move | uta.cse3310.Bot.BotII.movesToKing |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | The user can test if the game approparitely identifies a piece that is eligble for king, but the user cannot determine the number of moves/rows | Unable to test
16 | 34 | BotII shall increase the ELO rating for a move depending on how far away the piece is from becoming king | uta.cse3310.Bot.BotII.determineMoves |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable | Unable to test
17 | 34 | BotII shall increase the elo rating for a jump/capture move | uta.cse3310.Bot.BotII.determineMoves |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable | Unable to test
18 | 34 | BotII shall sort possible moves according to the selected strategy (aggressive or passive) based on their ELO ratings | uta.cse3310.Bot.BotII.implementBotStrategy |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable | Unable to test
19 | 34 | BotII shall select the highest ELO-rated move when playing aggressively and the lowest ELO-rated move when playing passively | uta.cse3310.Bot.BotII.implementBotStrategy |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This not testable | Unable to test
20 | 34 | BotII shall update its strategy during gameplay based on the current board state | uta.cse3310.Bot.BotII.playStyle |  | Untestable |  |  |  |  | Unable To Test |  |  |  | Not Testable | This is not testable by the user | Unable to test
21 | 34 | BotII shall switch to defensive strategy when at a numerical disadvantage | uta.cse3310.Bot.BotII.playStyle |  | Untestable |  |  |  |  | Unable To Test |  |  |  | Not Testable | This is not testable by the user | Unable to test
22 | 34 | BotII shall determine if thegiven board is a start board (i.e. BotII has made no moves and the opponent has made 0 or 1 moves) | uta.cse3310.Bot.BotII.isFirstMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
23 | 34 | BotII shall make a basic move if the given game board is a start game board | uta.cse3310.Bot.BotII.startMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 2, Steps 1-2 | Start a game player vs bot. The bot should make a move at the start of the game.
24 | 34 | BotII shall, before every move determination flush the moves object | uta.cse3310.Bot.BotII.requestMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
25 | 34 | BotII shall, for every piece that belongs to it, determine the moves that piece can make, add it to a list and sort that list by ELO rating | uta.cse3310.Bot.BotII.determineMoves |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
26 | 33 | Bot 1 shall use a fixed strategy to determine its moves when playing against the user or Bot II. | Bot1.java / requestMove() |  | Untestable |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 4, Steps 1-2 | Unable to test
27 | 33 | Bot 1 shall receive the current game board state from the Game Manager via the requestMove(Board board) method. | Bot1.java / requestMove() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
28 | 33 | Bot 1 shall return its selected move(s) to the Game Manager via the sendMove()method. | Bot1.java / sendMove() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
29 | 33 | Bot 1 shall communicate with the Game Manager via function calls | Bot1.java / requestMove(), sendMove() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
30 | 33 | Bot 1 shall be able to play against Bot 2 using the same interface. | Bot1.java / requestMove(), sendMove() |  | Test Not Working |  |  |  |  | test 3 step 4 |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Redundant, Req 10- covers this | User logs into website. Start a game bot vs bot. The bots should play each other until one of them wins or a draw occurs.
31 | 33 | Bot 1 shall not store any game state locally; all state will reside with the Game Manager. | Bot1.java / requestMove(), flushMoves() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
32 | 33 | Bot 1 shall correctly determine and evaluate all legal moves, including normal and capture moves, for all its pieces on the board. | Bot1.java / determineMoves(), playNormalMove(), playCapture() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 4, Steps 1-4 | Unable to test
33 | 33 | Bot 1 shall utilize a LinkedList<Move> to represent and manage sequences of moves, including potential chains for multi-jump captures. | Bot1.java / sendMove(), determineMoves() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
34 | 33 | Bot 1 shall avoid moves that expose its pieces to immediate counter-capture, especially in the passive strategy. The defensive strategy will lower the score of such moves to discourage risky decisions. | Bot1.java / passiveStrategyImplementation() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 4, Steps 1-4 | Unable to test
35 | 33 | Bot 1 shall send all move(s) to the Game Manager in a single transmission when multiple captures occur. | Bot1.java / sendMove() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
36 | 33 | Bot 1 shall follow the rules for the game that come from https://en.wikipedia.org/wiki/English_draughts | Bot1.java / requestMove() |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 4, Steps 1-4 | Start a game player vs bot. Play normally, the bot should only be able to make the same move the player is able to make.
37 | 33 | Bot I shall use this function to dynamically change the strategy depending on the output of countallPieces() | BotI.java / isAggressive() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
38 | 33 | Bot I shall count the board for all the pieces | BotI.java / countallPieces() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 4, Steps 1-4 | Unable to test
39 | 33 | Bot I shall play more aggressively (push forward more) if it has more pieces than the player. | BotI.java / aggressiveStrategyImplementation |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 4, Steps 1-4 | Unable to test
40 | 33 | Bot I shall play more cautiously if it has less pieces than player. | BotI.java / passiveStrategyImplementation |  | Untestable |  |  |  |  | work in progress |  |  |  | Not Testable | This is not testable by the user | Unable to test
41 | 33 | Bot I shall advance a space if the square is empty given that the space does not have an enemy piece on it. | BotI.java / playNormalMove |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test 4, Steps 1-4 | Start a game player vs bot. Play normally. The bot should move assuming there is no available jumps.
42 | 33 | Bot I shall evaluate and add a capturing move if the move exists and is legal. | BotI.java / playCapture |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 4, Steps 1-4 | The bot must jump a piece if there is a legal jump available
43 | 33 | Bot I shall identify whether a given move is a capturing move by evaluating the distance between the start and destination squares and checking for an opponent piece in between. | BotI.java / isCapturingMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | This is not testable by the user | Unable to test
44 | 33 | Bot I shall determine if a move places its piece in a vulnerable location where it can be captured by the opponent. | BotI.java / insideDangerRegion |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #5, Steps 1-4 | Unable to test
45 | 33 | Bot I shall evaluate if a given board position can be used by the opponent to attack. | BotI.java / canBeAttackedFrom |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #6, Steps 1-4 | Unable to test
46 | 33 | Bot I shall check if a move leaves the piece protected by an adjacent friendly piece. | BotI.java / hasBackupAfterMove |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #7, Steps 1-3 | Unable to test
47 | 33 | Bot I shall detect if a square is occupied by a friendly piece to determine support. | BotI.java / hasSupportAt |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #8, Steps 1-4 | Unable to test
48 | 33 | Bot I shall know the boundaries of the board so prevent plays made out of the board. | BotI.java / isInsideBoard |  | Test Working |  |  | Unable to Test |  | work in progress |  |  |  | Test 1: steps 6-12, Test 3: steps 4-8 | Test Case #9, Steps 1-4 | Start a game player vs bot. Play normally. The bot should not play a move that is out of bounds.
49 | 26 | The join game page shall display a waitlist of available players ready to play with their usernames and IDs in the order that the players joined under a section labeled 'Current Waitlist'. | joingame/Waitlist.js/displayWaitlist() | UI-JG-01 | Test Working |  |  | Test Working |  | test 1 step3 |  |  |  | Test 2 Steps 2 & 4 | Test Case #10, Steps 1-3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. in another tab in any browser, repeat steps 1-3
50 | 26 | The join game page shall display a button for a game against another user under a section labeled 'Choose a Game Mode'. | webapp/index.html | UI-JG-02 | Test Working |  |  | Test working |  | test 1 step3 |  |  |  | Test 1 Step 4, Test 2 Step 2 | Test Case #11, Steps 1-2 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game
51 | 26 | The join game page shall display a button for a game against a bot under a section labeled 'Choose a Game Mode'. | webapp/index.html | UI-JG-03 | Test Working |  |  | Test working |  | test 1 step3 |  |  |  | Test 1 Step 4, Test 2 Step 2 | Test Case #12, Steps 1-2 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game
52 | 26 | The program shall update the waitlist as players login and join/leave a game. | joingame/Waitlist.js/add(), joingame/Waitlist.js/remove() | N/A | Test Not Working |  |  | Test Working |  | test 1 step3 |  |  |  | Test 2 Steps 2 & 4 | Test Case #13, Steps 4-6 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. in another tab in any browser, repeat steps 1-3
53 | 26 | The join game page shall display a notification with updates to the waitlist under a section labeled 'Notifications'. | joingame/DisplayNotification.js/displayNotification() | UI-JG-04 | Test Not Working |  |  | Test Working |  | test 1 step3 |  |  |  | Test 2 Steps 2 & 4 | Test Case #14, Steps 1-3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game
54 | 26 | The join game page will display a notification indicating that the user is next to join a game under a section labeled 'Notifications'. | joingame/DisplayNotification.js/displayNotification() | UI-JG-05 | Test Not Working |  |  | Unable to Test |  | test 1 step3 |  |  |  | Duplicate requirement | Test Case #15, Steps 1-3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Player'
55 | 26 | The join game page shall have display a button to spectate a game of 2 bots playing against each other under a section labeled 'Choose a Game Mode'. | joingame/MatchMaker.js/requestSpectateBotVsBot() | UI-JG-06 | Test Working |  |  | Test Working |  | test 1 step3 |  |  |  | Test 1 step 4 | Test Case #16, Steps 1-2 | 1. Go to website http://su24.cse3310.org:9500/index.html 2. Either enter a user name that has 8 characters and includes at least one number and special character, or click generate random username 3. Click join game
56 | 26 | The join game page shall display new players and replaying players at the bottom (or start of the waitlist) under a section labeled 'Current Waitlist'. | joingame/Waitlist.js/displayWaitlist() | UI-JG-07 | Test Not Working |  |  | Uable to Test |  | test 1 step3 |  |  |  | Test 2 Steps 2 & 4 | Test Case #17, Steps 7-8 | 1. Go to website http://su24.cse3310.org:9500/index.html 2. Either enter a user name that has 8 characters and includes at least one number and special character, or click generate random username 3. Click join game
57 | 26 | The program will load usernames and IDs in waitlist and display them within 2 seconds of logging in/joining a game. | joingame/Waitlist.js/displayWaitlist() | N/A | Test Working |  |  | Test Working |  | test 1 step3 |  |  |  | Test 2 Steps 2 & 4 | Test Case #18, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Look in the Waitlist Display for the player's choosen username, and the ID associated with them 5.)Click Play v.s Bot 6.)Look in the Waitlist Display for the player's username, and ID as well as the bot's name and difficulty 7.)In a seperate tab repeat steps 1-4 8.)Click Play v.s Player 9.) Look for the username and ID of the current player and of the opposing player
58 | 26 | The web interface of the Join Game component will be written in HTML5. | webapp/index.html | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
59 | 26 | The program will be compatible with the web browsers Chrome and Firefox. | joingame | N/A | Unable to Test | Test 1 Step 3 Note: This requirement was modified to exclude Safari as this is not on Fedora. |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #19, Steps 1-4 | 1.) Open a Chrome Browser 2.)Go to website http://su24.cse3310.org:9500/index.html 3.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 4.)Open a FireFox Browser 5.)Repeat steps 2 and 3 6.)Open a Safari Browser 7.)Repeat steps 2 and 3
60 | 26 | The interactive and dynamic functionality within the component will be written in JavaScript. | joingame/Communication.js, Data.js, Displaynotification.js, MatchMaking.js, Waitlist.js | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
61 | 26 | When the button to play against another player is pressed, the program will send the player information along with the game mode to the Page Manager component to initalize the pairing up process to begin a game. | joingame/MatchMaker.js/requestPlayerMatch() | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #20, Steps 1-4 | Unable to test
62 | 26 | When the button to play against a bot is pressed, the program will send the player information along with the game mode to the Page Manager component to intialize the process to start a game against a bot. | joingame/MatchMaker.js/requestBotMatch() | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #21, Steps 1-4 | 1.) Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character. 3) After login,click on mode of game play vs Bot 4) Then the program will send the player information along with the game mode to the Page Manager component
63 | 26 | When a player(s) requests to join a game, the program removes their name from the waitlist. | joingame/Waitlist.js/remove() | N/A | Test Working |  |  | Test Working | [5 empty] | Test 2 | Test Case #22, Steps 9-10 | 1.) Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character. 3) After login,click on any mode of game like play vs player , play vs Bot ,Spectate Bot Vs Bot 4) Then the program removes their name from the waitlist.
64 | 26 | When a player(s) logins successfully, the program adds their name to the waitlist. | joingame/Waitlist.js/add() | N/A | Test Working |  |  | Test Working |  | test 1 step3 |  |  |  | Test 2 Step 2 & 4 | Test Case #23, Steps 11-12 | 1.) Go to website http://su24.cse3310.org:9500/index.html 3.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character. 3) As soon as you login, the player name can be found on waitlist.
65 | 26 | The program will receive player information (username and ID) from the Page Manager through a websocket. | joingame/Communication.js/handlePlayerData() | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
66 | 26 | The program will create a player instance based on the provided data from the Page Manager. | joingame/Data.js/constructor() | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
67 | 26 | The program will send player information (username and ID) and their selected game mode to the Page Manager through a websocket. | joingame/Communication.js/sendPlayerAttributes() | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | 1.) Go to website http://su24.cse3310.org:9500/index.html 3.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character. 3)After login,click on any mode of game like play vs player , play vs Bot ,Spectate Bot Vs Bot. 4) At the Notifications box below, the program will send player information and their selected game mode
68 | 26 | When the button to spectate a game of two bots playing against each other, the program will send players' username and ID along with the game mode to Page Manager to intialize the process to start the game | joingame/MatchMaker.js/requestSpectateBotVsBot() | N/A | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #24, Steps 1-3 | Unable to test
69 | 35 | After a game concludes, the players go to the end of the line waiting for the new game | GameTermination.java/checkGameOver() |  | Test Not Working |  |  | Unable to Test |  | work in progress |  |  |  | Test 2 Step 13 | Test Case #25, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
70 | 35 | The results of every game played will be stored into a database, and shall be used for building the contents of the leaderboard. | GameResult.java/saveResultsToDatabase() |  | Test Not Working |  |  | Unable to Test |  | work in progress |  |  |  | Not Testable | Cannot be tested by the user. | Unable to test
71 | 35 | The system will detect a draw, if one occurs | GameTermination.java/checkGameOver() |  | Test Not Working |  |  | Uable to Test |  | work in progress |  |  |  | Test 2 step 10 | Test Case #26, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until a draw occurs. Repeat steps 1-5 as needed until a draw occurs
72 | 35 | The system will have an understanding of the game rules in order to detect winnings after each play, and check for legalMoves to terminate the game | GameResult.java/checkForLegalMoves(), getWinner() |  | Test Not Working |  |  | Test Working |  | work in progress |  |  |  | Test 2 Steps 6-10 | Test Case #27, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
73 | 35 | The subsytem will send game termination information to database, only when the game ends through a final summary | GameTermination.java/saveResultsToDatabase() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
74 | 35 | The subsystem will send a final termination message to game play once a match is over | GameTermination.java/endGame(), sendResults() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
75 | 35 | The subsystem will handle a confirmation response from the database. | GameResult.java/confirmDataStored() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
76 | 35 | The subsytem will track the captured pieces, in order to determine who has lost the game | GameResult.java/trackCapturedPieces() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #28, Steps 1-3 | Unable to test
77 | 35 | The subsystem will keep track of the player scores after a move, as well as update them | GameResult.java/updateScores(), getScore() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #29, Steps 1-3 | Unable to test
78 | 27 | The game will run as a Java program with JavaScript/HTML clients. | Java WebSocket Server connection object in client JS |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
79 | 27 | The rules follow English Draughts from Wikipedia. | game_display_checkers.js/CheckersBoard.handle_checkers_piece_click() |  | Test Working |  |  | Unable to Test |  | test 1 step 4 |  |  |  | Test 2 Steps 6-10 | Test Case #30, Steps 1-3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Bot' 5. Play until the game finishes or crashes
80 | 27 | Display a standard 8x8 checkers board grid with alternating dark and light squares. Board layout should be clear and consistent, with the dark square at the bottom left corner. | game_display_checkers.js/CheckersBoard.update_board_style(), game_display_checkers.js/CheckersBoard.create_checkers_board() | UI011 | Test Working |  |  | Test Working |  | test 1 step 4 |  |  |  | Tests 2 Step 6-10 | Test Case #31, Steps 1-3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Bot'
81 | 27 | Display checker pieces for both players. Regular and king pieces should be visually different, and valid moves must be highlighted when a piece is selected. | game_display_checkers.js/CheckersBoard.update_board_style(), CSS styling in game_display_checkers.js/update_board_style() | UI012 | Test Not Working |  |  | Test Working |  | work in progress |  |  |  | Test 2 Step 6-10 | Test Case #32, Steps 1-4 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Bot' 5. Bring one of your pieces to the top border of the checkers field
82 | 27 | The game will allow selection of pieces and display valid move destinations by commuicating with other teams. Display feedback for illegal moves, captures, and multiple jump possibilities, as provided by other responsible teams to the game display team. | game_display_checkers.js/CheckersBoard.handle_checkers_piece_click(), game_display_checkers.js/CheckersBoard.show_possible_moves() | UI013 | Test Not Working |  |  | Uable to Test |  | Test1 step5 |  |  |  | Test 2 Step 4 | Test Case #33, Steps 1-4 | Unable to test
83 | 27 | Display current player's turn, player names (ID). | game_display_checkers.js/CheckersBoard.update_current_player(), game_id | UI014 | Test Not Working |  |  | Unable to Test |  | work in progress |  |  |  | Test 1/2 Step 6-10 | Test Case #34, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character. 3.) Click Join Game 4.) Select the mode of gameplay (Play v.s PLayer, PLay v.s Bot, or Bot v.s Bot). 5.) It displays the current turn and player names.
84 | 27 | Implement method for other teams to send messages to the players. | game_display_checkers.js/game_display_popup_messages() |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Cannot be tested by the user. | Unable to test
85 | 27 | Keep game board hidden until the game starts. Enable or disable move interface based on game state and player's turn. This must be controlled by page manager. | game_display_checkers.js/CheckersBoard.create_checkers_board() |  | Test Working |  |  | Test Working |  | work in progress |  |  |  | Test 1/2/3 Steps 2-3 | Test Case #35, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Look to make sure the game board is not displayed yet 5.)Select the mode of gameplay (Play v.s PLayer, PLay v.s Bot, or Bot v.s Bot) 6.)Once the player has joined a game, the game board should no longer be hidden
86 | 27 | Provide buttons for resigning, and offering draw. | game_display_checkers.js/handle_resign(), game_display_checkers.js/offer_draw(), game_display_checkers.js/add_game_display_user_control_event_listener() | UI015 | Test Working |  |  | Uable to Test |  | test 1 step 4 |  |  |  | Test 1/2/3 Step 4 | Test Case #36, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3)Click "Join Game" 4.) Select Play v.s Bot 5.)Look for the buttons underneath the board game
87 | 27 | Indicate who moves first. | game_display_checkers.js/CheckersBoard constructor, game_display_checkers.js/update_current_player() |  | Test Not Working |  |  | Test Working |  | work in progress |  |  |  | Test 1 step 4 | Test Case #37 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Player to join a game 5.)Look above the game board for a message indicating which player to move first 6.)Repeat steps 1-3 7.)Click Play v.s Bot 8.)Look above the game board for a message indicating if the player or the bot moves first 9.)Repeat steps 1-3 10.)Click Bot v.s Bot 11.)Look above the game board for a message indicating which bot moves first
88 | 27 | Display all valid moves for a selected piece. Valid moves are determined by backend and visualized on the board. | game_display_checkers.js/CheckersBoard.show_possible_moves(), game_display_checkers.js/return_allowed_moves(), game_display_checkers.js/is_valid_move() | UI016 | Test Working |  |  | Test Working |  | Test1 step5 |  |  |  | Test 1 step 6 | Test Case #38, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Player to join a game 5.)If it is the player's turn, select a peice owned by that player and check to see if it displays the moves that piece is able to make 6.)Click on an opponents piece to make sure the user isn't allowed to see their opponents current available moves
89 | 27 | Send all player moves to the backend. Game display collects and formats movement data. | game_display_checkers.js/CheckersBoard.move_checkers_piece(), WebSocket message: {type: "move", ...} |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #39, Steps 1-2 | Unable to test
90 | 27 | Support multiple concurrent game instances by designing the checkers board as a reusable class. | CheckersBoard class construction and design pattern |  | Unable to Test |  |  | Unable to Test |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #40, Steps 1-2 | Unable to test
91 | 27 | Automatically rotate the board 180 degrees for the black player to maintain player perspective. | game_display_checkers.js/CheckersBoard.rotateBoardIfBlack() |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 6-10 | Test Case #41, Steps 1-4 | Unable to test
92 | 27 | Implement robust error handling in UI functions with clear feedback. | Try/catch blocks, game_display_checkers.js/game_display_popup_messages() |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 1 Step 2 | Test Case #42, Steps 1-2 | Unable to test
93 | 27 | Define a standardized JSON message format for client-server communications with type-based message handling. | WebSocket message formatting in game_display_checkers.js/game_display_handle_websocket_received_data() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | none | Unable to test
94 | 27 | Automatically promote pieces to kings upon reaching the opponent's back row and update visuals. | game_display_checkers.js/move_checkers_piece(), game_display_checkers.js/update_board_style() |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 step 10 | Test Case #43, Steps 1-4 | Start game, either player vs player or player vs bot. Attempt to get one of your pieces to the back row of the board. When done, should automatically promote.
95 | 27 | Manage game state transitions and update UI appropriately during turn changes or game completion. | game_display_checkers.js/update_current_player(), game_display_checkers.js/game_display_handle_websocket_received_data() |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 steps 5-9 | Test Case #44, Steps 1-3 | Start game, either player vs player or player vs bot. When it is the player's turn, should display such on the webpage. The webpage should also display a message stating when it is not the player's turn.
96 | 27 | Notify players of game events such as opponent moves and game end. | Message handling in game_display_checkers.js/game_display_handle_websocket_received_data() |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 steps 5-9 | Test Case #45, Steps 1-4 | Start game, either player vs player or player vs bot. A message should be displayed when various events occur without the player adding extra input.
97 | 27 | Prevent duplication of event listeners. | game_display_checkers.js/register_buttons_to_event_listener() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #46, Steps 1-3 | Unable to test
98 | 36 | Game Play shall determine whether a move is legal or not and decides whether a piece has been captured. | GamePlay.GamePlay.returnBoard |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #47, Steps 1-7 | Unable to test
99 | 36 | A checker's piece shall not move to a spot taken by another checker's piece. If the user attempts to move in a spot that is taken send an error message to Game Manager | GamePlay.rules.isLegal |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 step 7 | Test Case #48, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click on PLay v.s Bot 5.)
100 | 36 | A checker's piece shall only move diagonally up the board unless it is marked by a crown, allowing the piece to move diagonally up and down. | GamePlay.rules.isLegal |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 step 6-10 | Test Case #49, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Player to join a game. 5.)On the user's turn, try and move a non-king piece directly above its current position (vertically) 6.) Move the piece to the next available diagonal square 7.) On the players next turn try to move the same regular piece backwards (first try moving vertically down then along the diagonal) 8.)Continue to play the game until one of the user's piece reaches the other end of the board, and is marked by a crown 9.)On the user's next turn attempt to move the crowned peice down to an available diagonal square, then attempt to move it up the board to an available square on the players next turn
101 | 36 | A checker's piece shall not move beyond the border of the playing field. | GamePlay.rules.inBounds |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 step 6-10 | Test Case #50, Steps 1-4 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Player' and wait until a player joins or repeat 1-4 in another tab 5. When you are able to move one of your pieces, drag or click them out of the checkers playing field
102 | 36 | Game Play shall communicate with Game Manager, notifying whether the requested move is legal and whether a piece has been captured. | GamePlay.GamePlay.returnBoard |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #51, Steps 1-4 | Unable to test
103 | 36 | A player shall not be allowed to move checker pieces of their oponent | GamePlay.rules.canMovePiece |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 4 Step 12 | Test Case #52, Steps 1-4 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Player' 5. repeat 1-4 in another tab while making sure your instances of the game are playing against each other 6. If 5 fails, repeat 1-5 7. When you are able to move one of your pieces, drag or click your opponent's checker's piece to another spot
104 | 36 | The user is able to make multiple successive jumps during one turn, if each jump captures an opponents piece and follows the rules associated with the user's cheker piece (i.e a king could do this in either a backwards or forwards direction, and a regular piece is only able to do this in a forward direction) | GamePlay.rules.isLegal |  | Untestable |  |  |  |  | work in progress |  |  |  | Test 2 6-10 | Test Case #53, Steps 1-4 | Unable to test
105 | 36 | The user must capture an opponent's piece if a legal move is presented/available | GamePlay.rules.isLegal / GamePlay.GamePlay.returnBoard |  | Test Working |  |  |  |  | Unable To Test |  |  |  | Not Testable | Test Case #54, Steps 1-4 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Player' 5. repeat 1-4 in another tab while making sure your instances of the game are playing against each other 6. If 5 fails, repeat 1-5 7. Lead to a position where a piece is able to capture an opponent's piece
106 | 36 | The bot should be subject to the same rules as the user | GamePlay.GamePlay.returnBoard |  | Test Working |  |  |  |  | Unable To Test |  |  |  | Duplicate requirement | Test Case #55, Steps 1-4 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Bot' 5. Play until the game finishes or crashes
107 | 36 | A king checker piece is not able to move both up and down during one turn. It must choose to either move up or down | GamePlay.rules.isLegal |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 11 | Test Case #56, Steps 1-4 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Bot' 5. Play until one of your pieces reaches the top border and becomes a king 6. Choose to move the king any direction 7. Try to do step 6 once more
108 | 36 | If the user is presented two different opportunities to capture an opponents checker piece during their turn, they are allowed to chose which checker's piece they capture | GamePlay.rules.isLegal |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 6-10 | Test Case #57, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player or Play v.s Bot to join a game. 5.)Play the game normally until an oportunity to capture 2 pieces simultaneously presents itself 6.) Choose 1 piece to capture and see if the game allows the move to be made 7.) Repeat steps 1-6 selecting the opposite side piece to capture (if left was captured previously, choose right)
109 | 36 | A king checker piece shall be held to the same capture rules as a regular checker piece. | GamePlay.rules.isLegal |  | Test Working |  |  |  |  | Unable To Test |  |  |  | Not Testable | Test Case #58, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player or Play v.s Bot to join a game. 5.)Play the game normally until an oportunity to create a king arises 6.) Position the king next to a valid opposing piece to capture 7.) Attempt to capture said piece
110 | 36 | A captured piece shall be removed from the game | GamePlay.rules.isLegal |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 6-10 & 12 | Test Case #59, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player or Play v.s Bot to join a game. 5.)Play the game normally until an oportunity to capture a piece arises 6.) 'Capture' said piece and inspect the board to see if the captured piece disappears
111 | 36 | A pieces move length shall be proportional to the amount of the opponent's pieces the moving piece jumps over. | GamePlay.rules.returnBoard |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 6-10 & 13 | Test Case #60, Steps 1-4
112 | 36 | GamePlay shall return a list of possible moves a player can take during their turn | GamePlay.GamePlay.returnMoves |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #61, Steps 1-4
113 | 31 | The PairUp subsystem shall allow the user to be matched with another user if the user desires to play against another user | PairUp/Matchmaking/pair |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 5 | Test Case #62, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Repeat Steps 1-3 in a different browser tab, keeping the original tab open 5.)Click Play v.s Player in both tabs
114 | 31 | The PairUp subsystem shall allow the user to be matched with a bot if the user desires to play against a bot | PairUp/Matchmaking/pair |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 step 5 | Test Case #63, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot to join a game.
115 | 31 | The PairUp subsystem shall allow a bot to play against another bot | PairUp/Matchmaking/pair |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 3 Step 3 | Test Case #64, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Spectate Bot v.s Bot to join a game.
116 | 31 | The PairUp subsystem shall manage a "matchmaking" pool with players that are looking for a match against another player | PairUp/Matchmaking/matching |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #65, Steps 1-4 | Unable to test
117 | 31 | The PairUp subsystem shall allow other subsystems to add/remove/search/clear players from the matchmaking pool | PairUp/PairUp |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
118 | 31 | The PairUp subsystem shall allow other subsystems to "ping" the matchmaking pool, which tells the matchmaker to look for possible pairs in the current pool | PairUp/ping |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
119 | 31 | The PairUp subsystem shall provide information of the two entities that were matched for a game to game manager | PairUp/Matchmaking/pair |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
120 | 31 | The PairUp subsystem shall keep track of information of players in queue, including their timeOfEntry, playerID, playerName, if their playAgainstBot, and wins | PairUp/PlayerInMatchmaking/N/A |  | Untestable |  |  |  |  | Unable To Test |  |  |  | Not Testable | NOT testable | Unable to test
121 | 31 | The PairUp subsystem shall keep track of all match information before sending it to game manager | PairUp/Match/N/A |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
122 | 31 | The PairUp subsystem shall implement a matchmaking algorithm to pair up players of the same skill range. The algorithm will instantly match those with a similar win count (+/- 1 win), but keep those that don't get matched instantly inside the matchmaking "pool". | PairUp/Matchmaking/matching |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #66, Steps 1-4 | Unable to test
123 | 31 | The PairUp subsystem shall ensure that no player gets stuck in matchmaking for eternity, if a match can be made. A player will have a "priority" once they have been in queue for more than 60 seconds, pairing them with the next player that enters queue, regardless of their win count | PairUp/Matchmaking/matching |  | Test Working |  |  |  |  | Unable To Test |  |  |  | Not Testable | Test Case #67, Steps 1-3 | Unable to test
124 | 31 | The PairUp subsystem shall keep track of all players in the queue, using a LinkedHashMap that stores playerID as a key, and the "PlayerInMatchmaking" object as its value | PairUp/Matchmaking |  | Untestable |  |  |  |  | Unable To Test |  |  |  | Not Testable | NOT testable | Unable to test
125 | 31 | The PairUp subsystem shall routinely check for possible matches to prevent a standstill scenario. An asychrounous scheduler is used to "ping" the matching method, telling it to check for available pairings between players currently in the queue every 60 seconds. | PairUp/MatchmakingScheduler |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
126 | 31 | The PairUp subsystem will support direct matches, in which a player directly challenges another player to avoid going through the matchmaking process | PairUp/PairUp/pair |  | Untestable | [8 empty] | Test 2 1-5 | Test Case #68, Steps 1-2 | Login to game. Should be able to directly challenge a specific account.
127 | 30 | The Database shall store player information and ranking of all users who create an account. | Uta.cse3310.DB.insertUser |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #69, Steps 1-4 | Unable to test
128 | 30 | The Database shall retrieve player account when page manager interface requests it by matching it to a players unique Username. | Uta.cse3310.DB.getLeaderboard |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #70, Steps 1-2 | Unable to test
129 | 30 | The Database will be created in SQLite3 | Uta.cse3310.DB. SQLiteConnector |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
130 | 30 | The Database shall update the rank for the winner and loser after a match has ended, which will be signaled by the game termination interface. | Uta.cse3310.DB. UpdatePlayer |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case #71, Steps 1-2 | Unable to test
131 | 30 | The Database shall display a query in which it orders all the accounts in ascending order by ranking having highest rank at the top. | Uta.cse3310.DB.getLeaderboard |  | Untestable |  |  |  |  | work in progress |  |  |  | Test 2 step 10 | Test Case #72, Steps 1-2 | Unable to test
132 | 30 | The query ranking the accounts shall be repeated after every match. | Uta.cse3310.DB.getLeaderboard |  | Untestable |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 73, Steps 1-4 | Unable to test
133 | 30 | The Database shall be updated, adding a new player if the player selects “create new account” button. Will also assign a unique ID to the player | Uta.cse3310.DB.insertUser |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 74, Steps 1-4 | Unable to test
134 | 30 | The database shall store player information which includes the username and Unique ID. | Uta.cse3310.DB.insertUser |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 74: steps 4)a,b | Unable to test
135 | 30 | The DB shall return an error message “username unavailable” if the username entered in the login interface matches any entries in the player table Database. | Uta.cse3310.DB.ValidateUser |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 Step 2 | Test Case 74: Steps 4)a | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character. Copy this Username 3.)Click Join Game 4.)Referesh the webpage and attempt to use the copied username
136 | 30 | The DB will return player information and player ID to Pair up interface when it is requested and verified that a pair up is possible between players by the Pair up interface. | Uta.cse3310.DB.ValidateUser |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
137 | 30 | The player ranking shall be a calculated with the following formula Rn = Ro + K(W-We) Rn is the new rating. Ro the old (pre-event) rating. K a constant (32 for 0-2099, 24 for 2100-2399, 16 for 2400 and above). W the score in the event - i.e. for a single match win=1; draw=0.5; lose=0. We the expected score (Win Expectancy), from the following formula: We = 1/ (exp10(-dr/400) + 1) dr equals the difference in ratings. | Uta.cse3310.DB.GetRank |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 75 | Unable to test
138 | 28 | A leaderboard will be displayed after each game | summary.html | U009 | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 76 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion | Summary:
139 | 28 | The results of every game played will be stored into a database. And shall be used for building the contents of the leaderboard | summary.js | U010 | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable
140 | 28 | The leaderboard page shall display a search bar to search players ranks | summary.html |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 77, Steps a-b | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion 5.)Attempt to search for a players name (yourself or another) in the searchbar
141 | 28 | The leaderboard page shall display the current players stats | summary.js |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 76 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
142 | 28 | The leaderboard page shall show a table that includes the top 100 players | summary.html |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 76 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
143 | 28 | The leaderboard shall display a players name, W/L, Wins, Losses, and Time played (most likely information) | summary.js |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 76 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
144 | 28 | The leaderboard page shall take information from the page manager and display that information | summary.js |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 76 | Unable to test
145 | 28 | The leaderboard shall be coded in html | summary.html |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
146 | 28 | The leaderboard shall rank players based off highest win loss ratio | summary.js |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 Step 10 | Test Case 76 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
147 | 28 | The leaderboard page shall have a back button that goes to main menu | summary.html |  | Test Not Working |  |  |  |  | work in progress |  |  |  | Test 2 step 13 | Test Case 78, Steps 1-2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion 5.)Once at the leaderboard page, click on the back button
148 | 29 | The system shall convert JSON messages from the frontend into Java objects and send them to the correct part of the backend (like the database, matchmaking, or game logic). It shall also convert Java objects back into JSON to send responses. | JSONconverter in pairup_subsys.java, UserEvent.java, App.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
149 | 29 | The backend shall be written in Java and shall communicate with the frontend, which is made using JavaScript and HTML. The system shall work on any web browser. | PageManager.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
150 | 29 | After a game concludes, a leaderboard will be shown using score data sourced from the gameplay session. | getUserScore() in Summary.java | [6 empty] | work in progress |  |  |  | Duplicate Requirement (139) | Test Case 76 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until conclusion
151 | 29 | The client interface will be a single HTML page that dynamically shows/hides relevant sections depending on the current game state. | Managed by frontend; enabled/disabled via received WebSocket events |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 2 Steps 1-5 | NOT testable | Unable to test
152 | 29 | All messages sent and received over WebSockets will be in JSON format, converted to Java using a custom JSONconverter. | public class App in App.java (extends WebSocketServer) |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
153 | 29 | After a player makes a move, the system shall check the new game state and send an update to the players involved. | game_status in game_status.java, handleMoveRequest() in PageManager.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 80, Steps 1-5 | Unable to test
154 | 29 | Each client that connects to the system shall be given a unique ID, which shall be used to send messages and manage game logic. | int clientId in App.java, linked via UserEvent.id |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
155 | 29 | The Java backend shall be event-driven. The GameManager shall run on a 1-second timer loop, and other parts of the system shall respond to events sent through WebSocket. | UserEvent in UserEvent.java, timer logic inside GameManager |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
156 | 29 | When the backend gets a move from the frontend, it shall check if the move is valid, apply it using the GameManager, and send the updated game status to both players. | handleMoveRequest(UserEvent) in PageManager.java, makeMove() in GameManager.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 81, Steps 1-5 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot to join a game. 5.)Make a move and wait for the board to update and reflect the subsequent moves
157 | 29 | If a player resigns, the system shall log the event in the GameManager and send a message to both players to confirm the resignation and end the game. | handleResign(UserEvent) in PageManager.java, processResign() in GameDisplayConnector.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 82, Steps 1-4 | Need two tabs or two players. Have both join a player vs player game. Have one of them resign the game by clicking the resign button. Both players should receieve a message stating that the player has resigned.
158 | 29 | If a player offers a draw, the system shall notify the other player. If the draw is accepted, the game shall end and both players shall be notified. | handleDrawOffer(UserEvent) and handleDrawAccept(UserEvent) in PageManager.java |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 4 Steps 5-7 | Test Case 83, Steps 1-3 | Need two tabs or two players. Have both join a player vs player game. Have one of them offer a draw. The other player should receive a message stating a draw is offered. The second player can then accept the draw to end the game.
159 | 29 | All event handler methods shall return a `UserEventReply` that includes a `game_status` object and a list of client IDs who should receive the message. | UserEventReply in UserEventReply.java, game_status in game_status.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
160 | 29 | On game start, a show_game_display event will be sent to each player with their ID, assigned color, and starting player information. | buildShowGameDisplay() in GameDisplayConnector.java |  | Test PARTIALLY Working |  |  |  |  | Unable To Test |  |  |  | Not Testable | NOT testable | Unable to test
161 | 29 | On game end (via win, resign, or draw), a hide_game_display event will be sent to all participants. | buildHideGameDisplay() in GameDisplayConnector.java |  | Test Not Working |  |  |  |  | Unable To Test |  |  |  | Not Testable | Test Case 84, Step 1 | Unable to test
162 | 29 | The backend must support relaying move_made_by_other_player_or_bot messages to ensure clients update pieces visually. | processMove() in GameDisplayConnector.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 80 | Unable to test
163 | 29 | Backend must support responding to get_allowed_moves requests and return a list of valid moves in valid_moves format. | processAllowedMovesRequest() in GameDisplayConnector.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  |  | Not Testable | NOT testable | Unable to test
164 | 29 | The backend shall be able to send `notify_players` messages for things like game wins or losses, connection issues, or error alerts. | buildNotifyPlayers() in GameDisplayConnector.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  |  | Not Testable | Test Case 85 | Unable to test
165 | 29 | The system shall return the game status for a player when given their player ID. | getGameinfo() in GameManagerSubsys.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
166 | 29 | The system shall retrieve game-related data such as the current turn, winner, loser, and draw status from the controller. | getGameinfo() in GameManagerSubsys.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 87, Test Case 86 | Unable to test
167 | 29 | Look up game sessions using client ID using GamePageController | getAllPlayerIDs(), processMove() in GamePageController.java |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
168 | 32 | The system shall have an object of squared data type for each individual board | GameManager/Board.getSquare, GameManager/Square.Square() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
169 | 32 | The board shall be a 2D array of Square objects | GameManager/Board.Board() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
170 | 32 | Move objects shall be linked list data structures to allow multiple steps in a single participant move | GameManager/Moves.Moves(), GameManager/move.Move() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
171 | 32 | The system shall manage the game state for each active match | GameManager/Game.progressGame() |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 steps 5-9, Test 2 Steps 6-10 | NOT testable | Unable to test
172 | 32 | The system shall enforce turn-based play using a boolean system | GameManager/Game.switchTurn() |  | Test Working |  |  |  |  | test 1 step 4 |  |  |  | Test 1 steps 5-9, Test 2 Steps 6-10 | Test Case 87 | Unable to test
173 | 32 | The system shall receive moves from players or bots and incorporate them from Square destination into the board | GameManager/Board.execute(), GameManager/Move.getStart()¦.getDest() |  | Test Working |  |  |  |  | test 1 step 4 |  |  |  | Test 1 steps 5-9, Test 2 Steps 6-10 | NOT testable | Unable to test
174 | 32 | The system shall place each player ID to their designated board and team once they're matched together | GameManager/GamePairController.newMatch() |  | Unable to Test |  |  |  |  | work in progress |  |  |  | Not Testable | NOT testable | Unable to test
175 | 32 | The system shall receive moves performed by Bot 1 and Bot 2 | GameManager/Game, GameManager/GameManager.requestBotMoves |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test Case 80 | Unable to test
176 | 32 | The system shall have colors of white and black randomly assigned to each player, where one is white and the other is black | GameManager/Game.Game |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 1 steps 5-9, Test 2 Steps 6-10 | Test 88, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot to join a game.
177 | 32 | The system shall update the score of the player after a piece is captured | GameManager/Player.addScore() |  | Test Not Working |  |  |  |  | work in progress |  |  |  |  | Test 89, Steps 1-4 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click either Play v.s Player, Play v.s Bot or Spectate Bot v.s Bot to join a game. 5.)Play the game normally until a piece is captured, paying attention to the score to ensure that it changes
178 | 32 | The system shall process a given Move object and respond with an disapproval alert if it is illegal | GameManager/GameManager.processMove() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 90, Steps 1–3 | Unable to test
179 | 32 | The system shall contain information of the position of the piece occupying a square | GameManager/Square.getRow()¦.getColumn() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 91, Steps 1–3 | Unable to test
180 | 32 | The system shall contain information of the type of piece occupying a square | GameManager/Square.getColor()¦.isKing() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 92, Steps 1–3 | Unable to test
181 | 32 | Move objects shall be utilized to encode the requested move from both players and bots | GameManager/Moves.makeMove() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable | Unable to test
182 | 32 | Checks whether the game is active | GameManager/Game.gameActive() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 93, Steps 1-4 | Unable to test
183 | 32 | Verfies whether slots are available to create a new game and creates one if so | GameManager/GameManager.createGame() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 94, Steps 1-4 | Unable to test
184 | 32 | Deals with game termination and notifies GameTermination | GameManager/GameManager.terminateGame() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 95, Steps 1-4 | Unable to test
185 | 32 | Deals with restarting the game | GameManager/GameManager.createGame() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 96, Steps 1-4 | Unable to test
186 | 32 | Initialises a new game with the relevant data to accomodate pairups | GameManager/GamePairController.newMatch() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 97, Steps 1-3 | Unable to test
187 | 32 | Deals with the piece count on the board | GameManager/Player.getPieces() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 98, Steps 1-3 | Unable to test
188 | 32 | Deals with the pieces taken | GameManager/Player.takePieces() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 99, Steps 1-3 | Unable to test
189 | 32 | PageManager shall be able to receive game ID's and the current board | GameManager/GamePageController.sendBoard() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
190 | 32 | GamePlay shall be able to access a list of moves | GameManager/GamePageController.processMove() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | NOT testable | Unable to test
191 | 32 | The system will support a maximum of 10 concurrent games | GameManager | U005 | Unable to Test |  |  |  |  | work in progress |  |  |  | Test 4 Step 13 | Test 100, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot 5.) Open 10 new windows and repeat steps 1-4 in each one
192 | 32 | Returns the game called by the searched player ID | GameManager/GamePageController.returnGame(), GameManager/GameManager.findGameByPlayerId |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable | Unable to test
193 | 32 | Tracks captures being made | GameManager/Game.lastCapture() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 101, Steps 1-2 | Unable to test
194 | 32 | Returns the winner and loser of the game | GameManager/Game.getWinner()¦.getLoser(), GameManager/GamePageController.getWinner()¦.getLoser() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 102, Steps 1-3 | Unable to test
195 | 32 | Updates the state of the board | GameManager/Game.updateBoard(), GameManager/Board.getSquare() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 103, Steps 1–2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot 5.) Play the game normally
196 | 32 | Checks whether the player is a bot or not | GameManager/Game.isPlayer1Bot()¦.isPlayer2Bot() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable | Unable to test
197 | 32 | Checks if a player is in an active game | GameManager/GameManager.isPlayerInGame() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable | Unable to test
198 | 32 | Returns active game count | GameManager/GameManager.getActiveGameCount() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable | Unable to test
199 | 32 | Removes a player from game if needed | GameManager/GameManager.removePlayer() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 104, Steps 1–3 | Unable to test
200 | 32 | Processes player requests to quit game | GameManager/GameManager.playerQuit() |  | Test Working |  |  |  |  | work in progress |  |  |  | Test 4 Step 10 | Test 105, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot 5.)When the user is notified that it is their turn, click the "resign" button
201 | 32 | Utilises pair made by GamePairController while creating games | GameManager/GameManager.createGame() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable | Unable to test
202 | 32 | Returns the player whose turn it is | GameManager/GamePageController.playerTurn() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 106, Steps 1–2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.)Click Play v.s Bot 5.)Look above the game board for a message notifiying the player whose turn it is
203 | 32 | Returns that the game was declared a draw | GameManager/GamePageController.getDraw() |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Test 107, Steps 1–3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Click generate random username or enter a username that the game accepts 3. Click join game 4. Click 'Play vs Player' 5. repeat 1-4 in another tab while making sure your instances of the game are playing against each other 6. If 5 fails, repeat 1-5 7. Offer draw on one instance of the website and accept on the other instance | Input box:
204 | 25 | The login page must provide a text input field for the user to enter their username. | input-box in loginHander.js | UI-LG-001 | Test Working | Test 1: Step 4 |  |  |  | Test1 step1 |  |  |  | Test 1/2/3 Steps 1-3 | Test 108, Step 1 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Observe the username tab, and then click on it 3.)Enter a random assortment of characters into that field
205 | 25 | Username must contain atleast 8 characters, 1 digit, and 1 special character. Message displays when requirements are not met with "Please match the required format" | onkeyup | UI-LG-002 | Test Working |  |  |  |  | test 2 step 2 |  |  |  | Test 1 Steps 1-3 | Test 109, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Enter a username that includes less than 8 characters 3.)Try to click the "Join Game" button 4.)Enter a username that includes 8 characters, at least one special character, and no numbers 5.)Try to click the "Join Game" button 6.)Enter a username that includes 8 characters, at least one number, and no special character 7.)Try to click the "Join Game" button 8.)Leave the username tab blank 9.) Try to click the "Join Game" button 10.)Enter a username that includes at least 8 characters, including at least one number and one special character 11.)Click "Join Game"
206 | 25 | Pattern to be used for the username requirements: /^(?=.*\d)(?=.*[!@#$%^&*])[A-Za-z\d!@#$%^&*]{8,}$/ | onkeyup |  | Test Working |  |  |  |  | Unable To Test |  |  |  | Not Testable | Test 110, Steps 1–3 | 1. Go to http://su24.cse3310.org:9500/index.html? 2. Enter a name that contains every typeable character that is on a QWERTY keyboard 3. Click join game | Container:
207 | 25 | There are constraints on special characters that can be used in username. If found any, give an error message with the instructions. | onkeyup, sendUsername() |  | Test Working |  |  |  |  | test 2 step 2 |  |  |  | Test 4 | Test 111, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Enter a username that includes at least 8 characters and a at least one number 3.) Use the special characters / \ in the username 4.)Try to click the "Join Game" button
208 | 25 | The login page shall display an alert if the username is invalid or missing upon form submission with the message "Please fill out this field". | joinGame() | UI-LG-003 | Test Working |  |  |  |  | test 2 step 3 |  |  |  | Test 1 Steps 1-3 | Test 112, Steps 1–2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Enter a username that includes less than 8 characters 3.)Try to click the "Join Game" button 4.)Enter a username that includes 8 characters, at least one special character, and no numbers 5.)Try to click the "Join Game" button 6.)Enter a username that includes 8 characters, at least one number, and no special character 7.)Try to click the "Join Game" button 8.)Leave the username tab blank 9.) Try to click the "Join Game" button
209 | 25 | The login page must have a button to "Join Game" once the user is done entering their username | button, .button-container, joinGame() | UI-LG-004 | Test Working | Test 1: Step 4 |  |  |  | test2 step 1 |  |  |  | Test 1 Steps 1-4 | Test 113, Steps 1–2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Observe the login page for the Join Game button
210 | 25 | Button hover shall darken the button to provide visual feedback on hover. | button:hoover | UI-LG-005 | Test Working |  |  |  |  | test 2 step 4 |  |  |  | Test 1 Steps 1-4 | Test 114, Steps 1–2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Observe the login page for the Join Game button 3.)Toggle over button
211 | 25 | Once the username is successfully submitted, the "join game" button should redirect the user to the game game. | joinGame() |  | Test Working |  |  |  |  | test2 step 8 |  |  |  | Test 1 Steps 1-3 | Test 115, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game | button hoover:
212 | 25 | Communications between the html pages and the java code will be via a websockets. | loginHandler.js, WebSocket |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable
213 | 25 | Websockets messages will be JSON encoded. | loginHandler.js, WebSocket |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable
214 | 25 | Logic performed by other subsystems in Java, not in HTML | index.html only has structure, JS logic is in loginHandler.js |  | Unable to Test |  |  |  |  | Unable To Test |  |  | Unable to Test | Not Testable | Not testable
215 | 25 | The login page shall validate the username in real time as the user types. | onkeyup |  | Test Working |  |  |  |  | test 2 step 5 |  |  |  | Test 1 steps 2-3 | Test 116, Steps 1-2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)enter at least 8 characters into the username section 3.)enter at least one special character into the username section 4.)enter at least one number into the username section
216 | 25 | The login page shall show validation rules when the input field is focused. | uInput.onfocus, #message |  | Test Working |  |  |  |  | test 2 step 5 |  |  |  | Test 1 Steps 2-3 | Test 117, Steps 1–2 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Click on the username tab
217 | 25 | Instruction is hidden, when pointer is not in the input box | uInput.onblur | UI-LG-006 | Test Working |  |  |  |  | test 2 step 6 |  |  |  | Test 4 | Test 118, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Click on the username tab 3.) Click on any part of the screen that is not the username tab | Instructions:
218 | 25 | The login page shall display ✓ or ✖ icons for each validation rule depending on input. | onkeyup, .valid, .invalid | UI-LG-007 | Test Working |  |  |  |  | test 2 step 5 |  |  |  | Test 1 Steps 1-4 | Test 119, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)enter at least 8 characters into the username section 3.)enter at least one special character into the username section 4.)enter at least one number into the username section
219 | 25 | The login page shall alert the user with "Joining Game" upon valid submission. | joinGame() | UI-LG-008 | Test Working |  |  |  |  | Test1 step 2 |  |  |  | Test 1 Steps 3-4 | Test 120, Steps 1-3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game
220 | 25 | The username shall be unique, no duplicate usernames allowed. | recieveFromPageManager(msg), message |  | Test Working |  |  |  |  | test 2 step 9 |  |  |  | Test 1 Step 2 | Test 121, Steps 1–3 | 1.)Go to website http://su24.cse3310.org:9500/index.html 2.)Either click generate random username or enter a username that has 8 characters that includes at least one number and special character 3.)Click Join Game 4.) In a seperate tab pull up the website and entire a the same log in that was entered previously
summary: